## Slide 1: MCB Butler Marine Corps Strategic Basing Program 3rd MLG, 3rd Men Bn, Surg Co B Basing Response Aug 1, 2025
CDR O’Connor, Justus
MCBB GF, Public Works Officer
315-645-2800
20250806 Installation Response KMedit
Controlled Unclassified Information
Controlled Unclassified Information
Consolidated Basing Request and Assessment Information is classified as
Controlled Unclassified Information.

## Slide 2: Basing Process, Actions, and General Timeline
Phase 1 - Validation
Phase 2 – Review and Assessment
Phase 3 - Selection
Phase 4 - Decision
Phase 5 – Execution/Reporting
Month 1
Month 2
Month 3
Month 6
Month 4
Month 5
Proponent Request Validated
Proponent Develops Requirements
Strategic Basing Working Group Brief (SBWG)
SBWG Comment/RFIs
Basing Action Provided to Region/Installation
Installation Response
Installation Assessment and Endorsements
COA Coordination/Selection with Proponent
Installation Outbrief to SBWG
Final assessment, COA selection, and staffing approval timeline is adjustable
COMMCICOM Review and Endorsement
DC I&L Decision or higher
Key:
Decision
Action
Controlled Unclassified Information
Notes:
(1) NEPA is assessed throughout basing process.
(2) Timelines are flexible based on action complexity and interdependencies.
(3) Congressional reporting, Host Nation Notifications, or Overseas Force Structure Change may be required.
Controlled Unclassified Information

## Slide 3: Assessment Process
Purpose – Installation Assessment
  To provide leadership COAs to support 3rd MLG, 3rd Medical Battalion, Surgical Company B relocation from MCB Hawaii to MCB Butler.
Strategic Narrative
  Facility Planner explored facility options for short-, mid-, and long-range solutions. The one short-term COA, which is recommended, recommends 3rd MLG consolidate functions in existing surplus facilities and re-absorb Surg Co B. Doing so would bring Role II capacities to the FIC. However, mid- to long-term solutions are currently unsupportable due to significant deficiency in programmed resources. DPRI Program of Record and OKICON re-development efforts do not account for the entirety of 3rd MLG subordinate Battalions to remain on Okinawa.
Impacts
  3rd MLG armory space is deficient and will require immediate unit funded procurement of portable armories (e.g. ARMAG).
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 4: Installation Planning
Assumptions
  No formal Basic Facilities Requirements (BFR) documented for SURG CO B on Camp Foster. Facility Planning factors were generated from existing SURG CO B Hawaii BFR, existing SURG CO A Camp Foster BFR, and TO/TE data.
  Other current 3D MLG units (3D MED BN, CLR 3, 3D LSB, 3D SUP BN, & MLG HQs) utilizing facilities aboard Camp Foster were also assessed.
  BFR calculations can typically be considered ideal ‘not to exceed’ targets. If facility utilization satisfies at least a significant portion of stated BFR requirements the general space assessment is considered ‘adequate’ for the planned unit/function.
  A future assessment will determine mid- to long-range requirements and Master Plan revision.
  SURG CO B target relocation aboard Camp Foster starts Q1 FY28.
Constraints
  Funding shortfalls and significant project backlog limits GF construction support in the target timeline.
  MCB Butler has a current shortfall of critical swing space (vacant facilities).
Restraints
  No user/unit facility movements shall be completed without MCB Butler notification/approval.
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 5: Functional Requirements Assessment
Armory/Weapon Storage Assessment:
SURG CO B Requirement: 944 SF
3D MED BN (current facilities) – (existing requirement):
  (809 SF) – (6,398 SF) = -5,589 SF Area Shortfall
3D MED BN currently has a significant armory capacity shortfall. Camp Foster does not have additional armory space available. It is likely that existing operational issues will be further impacted without mitigation.
Workspace/Office Assessment :
HQs / Administrative Office Facilities
SURG CO B Requirement: 4,063 SF
3D MED BN (current facilities) – (existing requirement):
  (27,031 SF) – (12,513 SF) = 14,518 SF Area Surplus
3D MED BN currently has a significant surplus of HQs/admin capacity. Surg Co B can be adequately co-located in existing 3D MED BN spaces and still result in a surplus of 10,455 SF.
Ground Equipment Maintenance Assessment :
SURG CO B Requirement: 2,848 SF
3D MED BN doe not exclusively utilize any Auto Org Shop facilities currently.
3D MED BN vehicle assets are maintained by other 3D MLG units. Initial assessment of Auto Org Shop facilities utilized by other MLG units aboard Camp Foster shows a significant surplus. Surg Co B can be adequately co-located in existing MLG facilities.
Billeting Assessment :
SURG CO B Total PN Loading: 181
  (139) Enlisted
  (42) Officer
UH Requirement (Unaccompanied) PN = 71
  (61) Enlisted
  (10) Officer
# of Dependents = 153
  (110) Spouse
  (43) Children
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 6: Functional Requirements Assessment
Utilities Assessment:
Specific facility-level utility requirements can be identified after scope is defined (eg buildings selected and conceptual floorplans created). This assessment reviewed base-level utilities impacts from the general facility requirements.
Per initial assessment no significant utility concerns.
Motorpool Assessment :
Tactical Vehicle Laydown Area
SURG CO B Requirement: 1,811 SY
3D MED BN does not exclusively utilize any Tactical Vehicle Laydown areas currently.
3D MED BN vehicle assets are maintained by other 3D MLG units. Initial assessment of Operational Vehicle areas utilized by MLG units aboard Camp Foster shows Surg Co B can be adequately co-located in existing MLG facilities.
Security/Classified Material Facility Assessment :
3D MED BN currently has SIPR capability. Surg Co B requirements can be adequately supported in existing facility.
Environmental & Historical Assessment: (Define how action may impact environment: i.e: new construction, new weapons, etc)
Insert Here
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 7: Functional Requirements Assessment
Airspace Management Assessment:
Not applicable
Airfield Operations Assessment:
Not applicable
Training Range/Facility & Simulator Assessment :
Applied Instruction Facility
SURG CO B Requirement: 1,776 SF
3D MED BN (current facilities) – (existing requirement):
  (3,139 SF) – (2,815 SF) = 324 SF Area Surplus
3D MED BN has a small surplus of classroom space. Surg Co B can be feasibly co-located in existing 3D MED BN spaces but likely to have some operational impacts. NOTE: existing training space is not optimized due to building deficiencies.
Fuel Assessments: (Define vehicle, generator, aircraft, or other fuel requirements)
Insert Here
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 8: Functional Requirements Assessment
MCCS & Quality of Life Assessment: (Define access to CDC, schools, exchanges, etc)
Insert Here
Medical Care Support Assessment : (Define specialized medical needs or requirements for uniform and dependants)
Insert Here
Fire & Emergency Services Assessment : (Define special FES requirements for airfield operation or installation)
Insert Here
Food Service Assessment : (Define food service such as mid-rats, normal chowhall operations, field requirements)
Insert Here
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 9: Functional Requirements Assessment
Contracting Assessment : (Define specialized contracting support from installation)
Insert Here
Supply Assessment :
Storage / Warehouse Facilities
SURG CO B Requirement: 800 SF (Camp Foster only)
3D MED BN equipment/materials supply storage is primarily supported by other 3D MLG units (eg MEDLOG Kinser). Limited storage space is exclusively utilized aboard Camp Foster currently.
3D MED BN / 3D MLG has a surplus of storage space available. SURG CO B can be adequately co-located in existing 3D MED BN and/or 3D MLG facilities.
Communications and Telephone Assessment: (Define communications or other frequency spectrum impacts/requirements):
Insert Here
Port/Pier Assessment : (Define port/pier or other water access requirements)
Insert Here
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 10: Courses of Action Assessment
COA 1:
(GF Installation Recommended) Work Facilities (short-range solution, 0 to 5-years)
SURG CO B functions are co-located in existing 3D MED BN and/or 3D MLG facilities aboard Camp Foster. MCB Butler provides limited support via facility turn-over(s) and re-assignment(s).
Recommend unit procured equipment (ARMAG) to mitigate armory shortfall.
Beyond 5-years, risk increases significantly due to DPRI POR
COA 2:
Work Facilities (mid-range solution, 10 to 15-years)
SURG CO B & 3d MED BN functions relocate due to DPRI POR. Potential to use vacated 3D MLG facilities aboard Camp Foster. Will require supporting project(s) starting in FY27 to convert facilities to 3d MED BN requirements.
  FY27 M2 Conversion for Instructional Facility
  FY27 M2 Expansion of Armory OR phased ARMAG unit procurement
  FY28 M2 Conversion of Warehouse to Climate Controlled Warehouse
COA 3:
Work Facilities (long-range solution, post 2048 OKICON)
SURG CO B & 3d MED BN functions relocate off-island per DPRI POR OR relocate to identified new development areas (KASA-1, CTA or NTA), requiring significant MILCON investment, as identified during Pacific Posture OPTs.
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 11: COA Summary of Findings
Criteria |  | COA 1 | COA 2 | COA 3 | COA 4 | Observations
General Assessment |  | Y | O | R | - | 
Capacity | Billeting requirements to include: UH for 71 permanent party pn |  |  |  | - | (61) Enlisted / (10) Officer calculated unaccompanied housing requirement.
 | Work Facility Requirements to include: 944 SF Armory 4,063 SF HQs / Admin 2,848 SF Veh Maint Shop 1,811 SY Vehicle lot 1,776 SF Training / Instruction 800 SF Storage / Warehouse | Y | O | R | - | COA 1 only provides a short-term, immediate solution. Mid- to long-range plans (COA 2 and COA 3) are not viable currently under DPRI POR. Requires prioritization and additional funding.
 | Access to utility distribution | Y | Y | R | - | 
 | Access to comm infrastructure |  |  |  | - | 
Environmental | Concerns/Issues |  |  |  | - | 
Costs | One-Time Facility upgrades/construction (USMC- funded) | $10K (ARMAG site prep & utilities hookup) | $25.2M | $100M | - | 
 | Sustainment (per ISA) |  |  |  | - | 
 | BOS (per ISA) |  |  |  | - | 
RED – Unsupportable (High Risk) Breaks US law, statute, etc. Cannot be accomplished with any amount of resources (time, money, personnel, etc.) ORANGE – Insufficient (Significant Risk) Existing or programmed resources are insufficient to support the initiative Cannot be achieved without significant modifications and/or additional programmed resources.
YELLOW – Executable (Moderate Risk) Can be accomplished but may require mitigation steps and solutions/resources be identified.
GREEN – Supportable (Low Risk) Achievable; no foreseeable obstacles exist that will preclude planned implementation.
Controlled Unclassified Information

## Slide 12: COA 1 Installation DOTMLPF/C
Pillar | Impact Assessment | Comments | Notes
Doctrine | G | No issues. | 
Organization | G | No issues. | 
Training/ Education | G | No issues. | 
Material (M) | Y | Require 6 new phones, computers, workstations.. | “M” – New material
Material (m) | G | No issues. | “m” – Existing material
Leadership and Communications Synchronization | Y | Requires phone lines and NIPR network capabilities to be installed and activated. There is a 2 month backlog in getting lines run and services activated. | 
Personnel | G | No issues. | 
Facilities | G | Minimal GF support required for facility turnover and re-assignment procedures. No impact to existing maintenance POR (FSRM). | Administrative support for facility assignment procedures.
Cost | G | Funding provided by HQMC DC xxx for all costs. | 
RED – Unsupportable (High Risk) Breaks US law, statute, etc. Cannot be accomplished with any amount of resources (time, money, personnel, etc.) ORANGE – Insufficient (Significant Risk) Existing or programmed resources are insufficient to support the initiative Cannot be achieved without significant modifications and/or additional programmed resources.
YELLOW – Executable (Moderate Risk) Can be accomplished but may require mitigation steps and solutions/resources be identified.
GREEN – Supportable (Low Risk) Achievable; no foreseeable obstacles exist that will preclude planned implementation.
Controlled Unclassified Information

## Slide 13: COA 2 Installation DOTMLPF/C
Pillar | Impact Assessment | Comments | Notes
Doctrine | G | No issues. | 
Organization | G | No issues. | 
Training/ Education | G | No issues. | 
Material (M) | Y | Require 6 new phones, computers, workstations.. | “M” – New material
Material (m) | G | No issues. | “m” – Existing material
Leadership and Communications Synchronization | Y | Requires phone lines and NIPR network capabilities to be installed and activated. There is a 2 month backlog in getting lines run and services activated. | 
Personnel | G | No issues. | 
Facilities | O | Surg Co B, 3d MED BN and bulk of 3d MLG not accounted for under DPRI POR. Requires significant M2R2 level FSRM investments into any remaining, unassigned facilities not yet demolished under DPRI POR. | 
Cost | G | Funding provided by HQMC DC xxx for all costs. | 
RED – Unsupportable (High Risk) Breaks US law, statute, etc. Cannot be accomplished with any amount of resources (time, money, personnel, etc.) ORANGE – Insufficient (Significant Risk) Existing or programmed resources are insufficient to support the initiative Cannot be achieved without significant modifications and/or additional programmed resources.
YELLOW – Executable (Moderate Risk) Can be accomplished but may require mitigation steps and solutions/resources be identified.
GREEN – Supportable (Low Risk) Achievable; no foreseeable obstacles exist that will preclude planned implementation.
Controlled Unclassified Information

## Slide 14: COA 3 Installation DOTMLPF/C
Pillar | Impact Assessment | Comments | Notes
Doctrine | G | No issues. | 
Organization | G | No issues. | 
Training/ Education | G | No issues. | 
Material (M) | Y | Require 6 new phones, computers, workstations.. | “M” – New material
Material (m) | G | No issues. | “m” – Existing material
Leadership and Communications Synchronization | Y | Requires phone lines and NIPR network capabilities to be installed and activated. There is a 2 month backlog in getting lines run and services activated. | 
Personnel | G | No issues. | 
Facilities | R | Surg Co B, 3d MED BN and bulk of 3d MLG not accounted for under DPRI POR. Requires significant MILCON investments into new development areas (KASA-1, CTA or NTA) that were identified at Pacific Posture OPTs. | Impact is Red because long term basing does not align with DPRI POR – not bilaterally agreed.
Cost | G | Funding provided by HQMC DC xxx for all costs. | 
RED – Unsupportable (High Risk) Breaks US law, statute, etc. Cannot be accomplished with any amount of resources (time, money, personnel, etc.) ORANGE – Insufficient (Significant Risk) Existing or programmed resources are insufficient to support the initiative Cannot be achieved without significant modifications and/or additional programmed resources.
YELLOW – Executable (Moderate Risk) Can be accomplished but may require mitigation steps and solutions/resources be identified.
GREEN – Supportable (Low Risk) Achievable; no foreseeable obstacles exist that will preclude planned implementation.
Controlled Unclassified Information

## Slide 15: Installation Assessment Way-forward
GF MCBB PW recommends COA 1 to meet the new basing requirement on a short-term basis, with notes below:
  The MCBB Program Of Record does not support 3D MED BN work facility requirements beyond 2030.
  Major conversion/repair/upgrade projects are possible but requires specified supplemental funding due to current FSRM program backlog. Planning/programming by FY26, Funding in FY27.
  GF space management actions completed NLT FY27 (facility space request, turnover, and re-assignment procedures).
Way-forward: GF MCBB PW recommends HQMC either engage DPRI to modify Program Of Record or invest in new development areas if a longer-term or enduring basing of 3D MED BN aboard MCBB is required.
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 16: Requests for Information
Provide RFI’s which must be addressed.
Controlled Unclassified Information
Controlled Unclassified Information

## Slide 17: Installation COA Recommendation
  COA 1 is the recommended option.
  COA 1 is the only feasible solution which provides adequate work facilities in the activation timeline. Risk significantly increases beyond 5 years if no additional facility mitigations are pursued.
  Immediate facility deficiencies can be mitigated via unit-procured equipment solutions, such as ARMAG storage containers.
  Facility conversion/repair/upgrade is possible, however requires supplemental FSRM funding, NLT Q2 FY27.
Controlled Unclassified Information

## Slide 18: Supporting Information
Controlled Unclassified Information

## Slide 19: Risk Definitions
RED – Unsupportable (High Risk)
  Breaks US law, statute, etc.
  Cannot be accomplished with any amount of resources (time, money, personnel, etc.)
ORANGE – Insufficient (Significant Risk)
  Existing or programmed resources are insufficient to support the initiative
  Cannot be achieved without significant modifications and/or additional programmed resources.
YELLOW – Executable (Moderate Risk)
  Can be accomplished but may require mitigation steps and solutions/resources be identified.
GREEN – Supportable (Low Risk)
  Achievable; no foreseeable obstacles exist that will preclude planned implementation.
Controlled Unclassified Information

## Slide 20: Butler Facility Planning Work Facility Requirements SURG CO B Planning Factors
No official updated BFR reported for Surgical Co B, however various documents were referenced to assume planning factors during this analysis.
SURG CO B (M28262) Facility Requirements |  |  | 
FACILITY CATEGORY TYPE | AREA RATED (BY CATEGORY) | AREA U/M | NOTES
ARMORY | 944 | SF | 1
STORAGE/WAREHOUSE | 3,500 | SF | 1,2
ORGANIC STORAGE | 800 | SF | 1,3
HQS/ADMINISTRATIVE | 4,063 | SF | 4
APPLIED INSTRUCTION | 2,815 | SF | 5
AUTO ORG SHOP | 2,848 | SF | 1
TACTICAL VEH LAYDOWN | 1,811 | SY | 1
Existing HI BFR, 2024
SURG CO MEDLOG requirement will be stored/maintained by MLG 3D SUP BN aboard Camp Kinser per MLG Basing Requirements Brief v9.
Organic Storage requirement (includes personal effects) should be maintained by parent command, 3D MED BN.
Company Headquarters requirements mirrors Surg Co A existing BFR, 2023.
Applied Instruction space requirements should roll up to the BN-level. Surg Co A and Surg Co B Applied instruction space consolidated and existing SURG CO A facility requirement supplemented with additional planning factor shown.

## Slide 21: Butler Facility Planning 1st Pass Analysis 3D MED BN Existing Condition
First pass analysis reviewed 3D MED BN existing facilities on Camp Foster to assess feasibility of parent command to internally mitigate the additional facility requirements for SURG CO B.
Armory space utilized is significantly below current requirement. Do not recommend consolidating SURG CO B armory in existing 3D MED BN armory.
Existing storage space utilized shows significant shortfall however target requirement may need further review if partial equipment storage is maintained by a different MLG unit (eg MEDLOG and/or H&S Co storage).
A significant surplus of Headquarter/Administrative space exists, consider re-utilization.
A surplus of Applied Instruction facility space exists, consider re-utilization.
No Auto Org Shop or Tactical Vehicle laydown facilities are currently utilized. These facility requirements are maintained by other MLG units (eg 3D LSB).
3D MED BN Existing Facilities |  |  |  |  |  |  | 
FACILITY NO | FACILITY USE | USE CATEGORY TYPE | AREA UTILIZED | AREA RQMT (BY CATEGORY) | AREA DELTA | AREA U/M | NOTE
225 | CAMP FOSTER ARMORY | ARMORY | 809 | 6,398 | -5,589 | SF | 1
5628 | COMM MAINT SHOP | STORAGE/WAREHOUSE | 8,266 | 28,333 | -20,067 | SF | 2
5717 | LSSS TAX CENTER/WIC/NMCRS/3 MLG | HQS/ADMINISTRATIVE | 13,998 | 12,513 | 14,518 | SF | 3
215 | CO HQ | HQS/ADMINISTRATIVE | 495 |  |  | SF | 
215 | BN HQ | HQS/ADMINISTRATIVE | 12,538 |  |  | SF | 
5628 | COMM MAINT SHOP | APPLIED INSTRUCTION | 667 | 2,815 | 324 | SF | 4
5628 | COMM MAINT SHOP | APPLIED INSTRUCTION | 2,472 |  |  | SF | 

## Slide 22: Butler Facility Planning 1st Pass Analysis Summary / Recommendations
Locating SURG CO B aboard Camp Foster does not align with the long-range Installation Master Plan, therefore recommend temporary assignment to re-utilize existing facilities with potential minor construction support, where required.
  Armory – Recommend additional facilities beyond existing 3D MED BN utilization to meet SURG CO B requirements. However, bldg. 225 is the only armory on Camp Foster – it is a consolidated facility supporting various MCIPAC and III MEF tenants and fully occupied. May require MLG/MEF adjudication of priorities and potential space re-distribution. Alternatively, a temporary facility (ARMAG) solution should be considered as a MEF equipment procurement mitigation.
  Storage / Warehouse – Adequate organic storage space exists within 3D MED BN warehouse, bldg. 5628. General warehouse requirements (such as MEDLOG storage) will need supplemental support in facilities assigned to other MLG units. Initial assessment shows that 3D MLG has available surplus space to adequately mitigate.
  HQs / Administrative – 3D MED BN has significant surplus of existing office space. Recommend re-distributing existing spaces in bldg. 215 and/or 5717 to locate SURG CO B requirements.
  Applied Instruction – A small surplus of training space exists currently, recommend re-distribution of space(s) in 5628 to locate SURG CO B requirements. NOTE: 5628 is not currently configured to support training ops. Recommend minor construction project to convert functional areas (primarily HVAC upgrades).
  Auto Org Shop / Tactical Veh Area – Currently no assets are assigned explicitly to 3D MED BN. However other 3D MLG units maintain the existing requirements. Initial assessment shows MLG has surplus to take on the additional SURG CO B requirements.
With regards to working facility requirements, a temporary basing in the timeframe aboard Camp Foster is feasible. SURG CO B facility requirements can be adequately mitigated by re-distributing existing 3D MED BN / 3D MLG utilizations.

## Slide 23: Butler Facility Planning 1st Pass Analysis Installation Master Plan Notes
The Installation Master Plan does not include an enduring requirement for 3D MED BN aboard Camp Foster. Under DPRI OKICON current 3D MED BN and 3D MLG work facilities are impacted in later phases by site clearing demolitions or divestment by land return. The POR end state relocates all 3D MLG functions off Camp Foster to Camp Hansen/Guam/Hawaii.
Further analysis/advanced planning is required to identify necessary mitigation steps and additional resources required for mid- and long-range plan components.
Existing 3D MLG units aboard Camp Foster have significant space deltas recorded in the facility database (INFADS). These mostly originate due to improperly executed large-scale re-organization efforts in recent years by 3D MLG subordinate units. A number of 3D MLG units are operating from buildings without documentation or notification to Butler GF – this negatively impacts normal maintenance/sustainment planning, execution of new Force Design requirements, and existing space management or new basing efforts such as Pacific Posture.